## Project Budget
Project Budget Template
Project Name: | Alpha Omega
Department: | Marketing
Supervisor Name: | Oliver Jones
|  |  |  | Labor |  | Materials |  |  |  | Fixed |  |  |  | BALANCE
|  |  | Planned Hours | Actual Hours | $/HR | UNITS | $/UNITS | Travel | Equipment |  | Misc. | BUDGETED | ACTUAL | UNDER/OVER
WBS | Project Tasks | Assigned To: | [9 empty] | 700 | 1590 | -890
1 | Task | Dave Johnson | 8 | 8 | 30 | 100 | 5 |  |  | 50 |  | 300 | 790 | -490
2 | Task | Sarah Goldman | 8 | 8 | 15 |  |  | 30 |  | 100 |  | 300 | 250 | 50
3 | Task | Melissa Shaw |  |  |  | 50 | 11 |  |  |  |  | 100 | 550 | -450
3.1 | SubTask | [10 empty] | 0 | 0 | 0
3.2 | SubTask | [10 empty] | 0 | 0 | 0
3.3 | SubTask | [10 empty] | 0 | 0 | 0
3.4 | SubTask | [10 empty] | 0 | 0 | 0
4 | Task | [10 empty] | 0 | 0 | 0
5 | Task | [10 empty] | 0 | 0 | 0
| SUBTOTAL |  |  |  | 360 |  | 1050 | 30 |  | 150 | 0 | 700 | 1590 | -890
Free Related Templates
Project plan template for Word
Gantt chart template for Excel
Project dashboard template for Excel

## How to Use this Template
Introduction
Use this project budget template to track all of your project expenses at a task level. Simply enter data into the fields, and your over/under will be automatically calculated. Remember, a successful project is one that comes in under budget.
Definition of Terms
WBS: Work breakdown structure lets you see the hierarchy of tasks as a number
Task: Enter the name of the task being worked on.
Assigned To: Who is responsible for the task
Planned HR: Enter the number of hours you expect the task to take.
Actual HR: Enter the number of billable hours the work actuallty took.
Labor $/HR: Enter how much money per hour that labor cost you.
Materials UNITS: Enter how many units of material you needed to complete the task.
Materials $/UNITS: Enter how much money each unit cost.
Travel: Enter the total travel expenses.
EQUP/SPACE: Enter how much your equipment or office space costs.
FIXED: Enter any costs that are fixed and unchanging.
MISC: Enter any other known costs.
BUDGET: Enter your budget for the task.
ACTUAL: This field will be automatically calculated based on the other costs entered in the row.
UNDER/OVER: This will be automatically calculated based on the budget vs actual fields.
SUBTOTAL: This row sums all the rows above it to give you a subtotal for the project.